## Sheet1
National Risk Regster for ITE AY24-25
ID | Risk | Details | Mitigation | Likelihood | Impact | Risk Score | Comments
1 | Quality | Due to school budget constraints, there may be less capacity to undertake ITE work in schools which will impact on student teacher learning and experience as well as limit the time available for effective mentoring. | Additional support and resource to support school involvement in ITE. Pooling of resource and expertise by USCET members. | 4 | 4 | 16
2 | School placements | Because schools' capacity to accept placements is limited (as a result of budget constraints and/or staff shortages), there is a risk that there will be students left without placements, that placements are undertaken in schools at pace (without usual training) or that the most effective schools are not deployed. This risk is heightened in areas where mutliple ITE providers operate. | Encouragement and levers for schools to engage with ITE. Allowing schools in Estyn categories to contribute. Request that LAs, relevant national bodies and professional associations encourage schools to participate. Allow greater flexibility at provider level and length of placements and use of alternative models. | 4 | 4 | 16
3 | Financial | Student fees are insufficient to support HEI costs and PGCE programmes usually offer low contribution rates. If universities are required to rationalise provision and prioritise financial planning for programmes, ITE providers may not be able to operate. This is also likely to have a wider impact on HEI education provision more widely due to the synergistic nature of provision and the structure of staffing models. | Ensure fees are on a par with other parts of the UK. USCET members to negotiate contribution rates that reflect the fact that ITE students spend much time off campus and so do not access university resources. WG to contribute to school placment costs. | 3 | 5 | 15
4 | Retention | Reduced quality of school experience and increased operating challenges in school may mean student teachers find learning to teach very challenging. leading to higher withdrawal rates and/or poor student wellbeing. | Pooling of expertise and advice on supporting of students on placement. Greater focus on well being of students, and ensuring they are not isolated. Realistic expectations in terms of workload. Advice to head teachers (from ITE sector, LAs, Estyn and WG) on providing a nurtering environment for student teachers in schools. | 3 | 3 | 9
5 | Recruitment | Negative media portrayal and perceptions of teaching as a very difficult professional career may discourage applicants from applying to the PGCE. | WG and others to promote taeching as a career more effectively. Professional bodies to talk up the profession. Identify good news storires for the press and social media. | 3 | 3 | 9
6 | Financial | Significantly more funding for mentoring support in schools and teaching incentives is provided by the DfE to enhance the quality of mentoring in ITE and attract recruitment. There is a risk that policy implementation and quality outcomes across England and Wales will be compared, without consideration for the financial resource available to support provision in each jurisdiction. It may also pose an equity risk to students who choose to study in Wales. Risks to recruitment may also arise as PGCE candidates may opt for English ITT due to a perception of greater support available through bursaries and in-school support. | Secure parity of funding with England, through diversion of existig budgets if necessary. ITE placements to be seen as part of school improvement activities and supported accordingly. | 3 | 3 | 9
7 | Workforce | Low levels of staff morale, poor wellbeing or workload concerns within both school-based and university-based teacher educator workforce may reduce engagement and productivity within ITE. | HEIs to support well being and mental health of ITE staff. Reduce burdens of regulatory processes. | 3 | 4 | 12
8 | Quality | Multiple regulatory frameworks increases the workload activity of partnerships to meet demands. This may result in reduced capacity for partnership working as a result of agreed time being utilised for participation in regulatory activity instead. | Concrete, measurable and solutions focussed actions to reduce unmanageable burdens. Estyn and EWC to recognise that a real problem does exist and take actions that go further than tinkering at the edges. WG to force a solution if necessary. | 4 | 4 | 16
9 | Policy | If regulatory arrangements continue in their current form, there may be increasing divergence from models of self-evaluation and accountability elsewhere in the education system and partnerships may continue to operate within a performative, high-accountability model. | As above. | 4 | 3 | 12
10 | Policy | If ITE structures are changed without accompanying policy, process and resources for other parts of the system, a genuine model of joint accountability will be limited in its effectiveness. | WG and others consult USCET about all policy areas that might impact on ITE in advance. WG to address internal 'silo' issues. | 3 | 3 | 9
11 | Policy | If too much emphasis is placed on the role of ITE as a means of policy implementation and school improvement, it is likely to lead to over-inflated accountability being placed on ITE partnerships and a perception that provision is not meetings all aims. | As above, plus introduce a requirement that any additional expectation placed on ITE providers is offset by removing an existing expectation that requires a comparable input of resource. More attention to also be applied to the role of CPD in upskilling teachers. | 3 | 3 | 9
12 | Curriculum | If there is an expectation for continual additions or changes to the ITE curriculum as set out in the accreditation criteria (for example, in response to current political, Estyn or pressure group priorities), then the already stretched curriculum will become even more intense, may increase the workload pressures on PGCE students and reduce the depth of student study. Over time, it may result in the curriculum lacking cohesion. | As above. | 4 | 3 | 12
13 | Recruitment | UCAS is used for applications for both undergraduate and postgraduate teaching in Wales. The UCAS system was established for undergraduate programmes and does not meet the requirements for postgraduate in relation to number of choices, dates and deadlines. The previous system GTTR was better as allowed sequential applications and more flexibility around dates and deadlines. UCAS is well known for undergraduate programmes not postgraduate programmes and since changes have not been made to their system to accommodate a separation for postgraduate this leads to confusion for some applicants and may be deterring them from applying. There is also an application fee unlike the DfE Apply system in England which could be a barrier for certain applicants. | A bespoke application system for Wales for postgraduate teacher training, the same as what is in operation in Wales with the DfE Apply system. | 3 | 3 | 9
| Quality | Mentoring is a continually recognised area of development for partnerships in both ITE and induction phases by regulators. If the status given to the role of mentors is not raised, or increased support and resource provided for this role, it is likely that mentoring will continue to be variable across schools in Wales and remain to be an identified improvement area. This also increases the reputational risk to ITE partnerships who may have invested siginifcantly in support for mentoring which is hampered by issues outside of their control and is publically reported. | Recognition of the context of mentoring and the operational challenges faced by schools in releasing staff for training and to give sufficient time for mentoring. Raise the status through recognising mentoring as a leadership and improvement activity within the school either through time or financial remuneration which matches the importance and responsibility to the profession. | 3 | 5 | 15
| Professional learning | HEIs, including partnerships, have previously played an important role in supporting the professional learning landscape for teachers at all stages in Wales. If it is not clear how HEIs are intended to contribute to the new professional learning offer or integrated within plans following the middle tier review, there may be a lack of systematic and structural processes in place to engage HEI support in PL in cohesive and effective way. |  | 3 | 3 | 9
| Policy and Operations | Close collaboration with regional consortia and partnerships forms part of accredited requirements as well as developing a continuum of learning between ITE and Induction. As it not yet known by partnerships what will replace consortia or their roles and responsibilities, this hinders long term planning for development. It also poses internal HEI policy risks as partnerships may need to make changes to remain compliant with partnership validation policy. |  | 4 | 4 | 16
| Research | If the role of partnerships and HEI providers more broadly are not made clear, there is a risk to the successful implementation of the NSERE. Increasing financial constraints within HEIs and schools may limit capacity and/or engagement with educational research. This may pose risks to the development of an evidence-informed profession and, in the longer term, impact detrimentally on the REF 29 submission for education UoA in Wales. |  | 4 | 4 | 16
| Welsh language | If Welsh language skills do not increase or improve in earlier stages of education (e.g. learning Welsh at school, uptake at A level, undergraduate provision etc) then there will be a reduced and/or declining pool of candidates eligible for post-graduate study to become a teacher through the medium of Welsh. It may become increasingly difficult for partnerships to recruit for Welsh medium provision posing a risk to the finacial viability of WM routes and/or increasing the risk of failing to meet aspirational targets of 30% of ITE students preparing to teach through the medium of Welsh. If teaching as a profession is not viewed as an attractive career choice for Welsh speakers, then it may become more difficult to recruit in a competitive public sector and business environment. |  | 4 | 4 | 16